## Sheet1
UTSTAGE-SQL-01 | 2022-07-11 |  | UT-SQLSTG-01 |  |  | UTQA-SQL-14
1 | Stop all Staging Unitrac Services | SA | Databases to Refresh |  | Databases to Keep As Is | Databases to Refresh |  | Databases to Keep As Is
2 | Detach DATA FILES AND LOG FILES for ActiveDiagrams,BSSMessageQueue,DBA,HDTStorage,LIMC,PerfStats, UnitracHDStorage,VehicleCT, VehicleUC and Copy to E: Drive | DBA
3 | Drop all F: User Databases on UTSTAGE-SQL-01 | DBA | LetterGen |  | ActiveDiagrams | archiveEDI |  | BSSMessageQueue
4 | Disable All DBA Jobs | DBA | OperationalDashboard |  | BSSMessageQueue | EDI |  | DBA
5 | Stop SQL Services on UT-SQLSTG-01 | DBA | OspreyDashboard |  | DBA | LetterGen |  | HDTStorage
6 | Disable SQL Services on UT-SQLSTG-01 | DBA | PredictiveAnalysis |  | HDTStorage | OperationalDashboard |  | LFP
7 | Present new drive snaps from production to UT-SQLSTG-01 | Infrastructure | QCModule |  | LIMC | OspreyDashboard |  | LIMC
8 | Delete all TempDB Files presented in new snap | DBA | SADashboard |  | PerfStats | QCModule |  | PerfStats
9 | Copy ActiveDiagrams,BSSMessageQueue,PerfStats, VehicleCT, VehicleUC DATA and LOG FILES back to F: drive before SQL restart. Replace the files from prod if they exist. | DBA | UniTrac |  | UnitracHDStorage | SADashboard |  | UnitracHDStorage
10 | Restart SQL Services on UT-SQLSTG-01 | DBA | UniTrac_DW |  | VehicleCT | UniTrac |  | VehicleCT
11 | Assign UT-SQLSTG-01\Administrators group full control of all data files before attaching (if not already granted) | DBA | UniTrac_Maintenance |  | VehicleUC | UniTrac_DW |  | VehicleUC
12 | OPEN SSMS as Administrator!!!!!! | DBA | UniTracArchive |  |  | UniTracArchive
13 | Reattach all newly presented database files | DBA | VUT |  |  | VUT
14 | Reattach ActiveDiagrams,BSSMessageQueue,PerfStats, VehicleCT, VehicleUC | DBA
15 | Restore UTSTAGE-UTL1 UTL database from UTL-SQL-01 DDBoost Full Backup | DBA
16 | Restore MongoDB UTLCache database from Prod Cluster Backup | DBA
17 | Run Fix SQL Login script in both UTL and Unitrac | DBA | Drives: |  |  | Drives:
18 | Run DBUtility.exe to sync UTL data | SA
19 | Execute Refresh Scripts against Unitrac database on UT-SQLSTG-01 (making sure to update server name) | SA | C: (System) | 100GB |  | C: (System) | 150GB
20 | Execute Refresh Scripts against UTL database on UTSTAGE-UTL1 | SA | E: (Programs) | 100GB |  | D: (Programs) | 110GB
21 | Quick DBA Review of Refreshed Environment | DBA | F: (Mounts) |  |  | E: (Mounts)
22 | Restart Staging Unitrac Services | SA | F:\SQL\Data01 | 6.5TB |  | E:\SQL\Data01 | 5.3TB
|  |  | F:\SQL\Data02 | 6.5TB |  | E:\SQL\Data02 | 5.3TB
UTQA-SQL-14 | 2022-07-18 |  | F:\SQL\Data03 | 6.5TB |  | E:\SQL\Data03 | 5.3TB
|  |  | F:\SQL\Data04 | 6.5TB |  | E:\SQL\Data04 | 5.3TB
1 | Stop all QA Unitrac Services | SA | F:\SQL\Data05 | 10TB |  | E:\SQL\Data05 | 8.3TB
2 | Detach DATA FILES AND LOG FILES for BSSMessageQueue,DBA,HDTStorage,LFP,LIMC, PerfStats,UnitracHDStorage, VehicleCT, VehicleUC and Copy to E: Drive | DBA | F:\SQL\Data06 | 2TB |  | E:\SQL\Data06 | 2.1TB
3 | Drop all F: User Databases on UTQA-SQL-14 | DBA | F:\SQL\SQLLogs | 1TB |  | E:\SQL\SQLLogs | 1TB
4 | Disable all DBA Jobs | DBA | F:\SQL\TempDB | 300GB
5 | Stop SQL Services on UTQA-SQL-14 | DBA |  |  |  | G: (TempDB) | 300GB
6 | Disable SQL Services on UTQA-SQL-14 | DBA |  |  |  | K: (PerfMon) | 40GB
7 | Migrate UTQA-SQL-14 to DataBank (ip address will change) | Infrastructure |  |  |  | Q:(Mounts) | 200GB
8 | Present new drive snaps from production to UTQA-SQL-14 | Infrastructure
9 | Copy DBA,BSSMessageQueue,HDTStorage,LFP,PerfStats,UnitracHDStorage, VehicleCT, VehicleUC DATA and LOG FILES back to F: drive before SQL restart. Replace the files from prod if they exist. | DBA
10 | Restart SQL Services on UTQA-SQL-14 | DBA
11 | Assign UTQA-SQL-14\Administrators group full control of all data files before attaching (if not already granted) | DBA
12 | OPEN SSMS as Administrator!!!!!! | DBA
13 | Reattach all newly presented database files | DBA
14 | Reattach DBA,BSSMessageQueue,HDTStorage,LFP,PerfStats,UnitracHDStorage, VehicleCT, VehicleUC | DBA
15 | Restore UTQA-UTL1 UTL database from UTL-SQL-01 DDBoost Full Backup | DBA
16 | Restore MongoDB UTLCache database from Prod Cluster Backup | DBA
17 | Run Fix SQL Login script in both UTL and Unitrac | DBA
18 | Run DBUtility.exe to sync UTL data | SA
19 | Execute Refresh Scripts against Unitrac database on UTQA-SQL-14 (making sure to update server name) | SA
20 | Execute Refresh Scripts against UTL database on UTQA-UTL1 | SA
21 | Quick DBA Review of Refreshed Environment | DBA
22 | Restart QA Unitrac Services | SA